Ballot Site Project Plan

This is a website application for balloting or voting in which a set of entities (names of people or names of voters) are shuffled randomly and user would have to pick one of these entities.

Project Planning phase Period: 23rd June to 25th June 2023.

Project Planning phase Time Frame: 10 hours, 4 hours a day except Sunday.

Project Execution Period: 26th June to 9th July 2023.

Project Execution Time Frame: 4 hours a day except Sunday which has 2hours and the 4 hours can be shared into two halves of 2 hours.

Sub Plans:

- Quality Plan:

- A Formal Platform.

- Contain Little Content.

- Contain a help option.

- Easy to use.

- Validation Plan:

- Users should be able to move from one page to the next.

- Users should select just one entity.

Project Constraints:

- Programmer is not too good in web languages and will have to learn.

- A User should select just one entity which is not the user.

Risks

- Risk Identification

- Programmer gets bored of the project.

- Changes in the requirements of the project.

- Some Components may not be completed on time.

- Network Disturbance.

- Insufficient internet data bundle.

- Underestimated size of the software and difficulty of implementation.

- New technology may come up which are better than what was used in this project.

- Programmer gets busy with other commitments.

- Programmer may need to learn part of the programming languages before implementing.

- Consistency of the software across various platforms.

- Risk Analysis

Prioritizing risks;

h, (c, i), d, e, a, f, b, g

- Risk Plan

h: - Prepare well stated milestones and deliverables for each part of the project.

-Plan the activities before the next day of work (list deliverables and tasks).

- Set Alarms for tasks and milestones.

c,i: - Prepare all the possible technologies to work on a component before working on it.

- Include tests during the project development.

- Work during hours of less distraction (morning or night).

- Set deliverable alarms.

- Prepare the steps required to implement a component.

- Download and/or learn the things necessary for implementation the day before or hours before.

d: - Buy Camtel data bundle.

- Buy other bundles from other ISP’s

e: - Change Location(School or home)

- Change ISP.

a: - Have regular breaks within the two hours of work (or also after every deliverable).

- Set prizes after each milestone.

- Do tests to see output.

f: - Study the implementation of a component hours or days before implementation on stackoverflow or youtube.

- Overestimate the size and difficulty of the component implementation.

- Study properties of component before implementation.

b: - Don’t add document requirement modification.

- Remove any annoying requirement.

g: - Use modern frameworks and libraries.

- Risk Monitoring

Risk Assessment Document

| Risk id | Effect | Current Solution |
| --- | --- | --- |

New Risks: ……………

Hardware and Software Resource Requirements

- Hardware Requirement:

- Computers (MacBook, Windows).

- Phones (IOS, Android)

- Server

- Software Resource Requirement:

- Development Technologies:

HTML, CSS, JavaScript, Typescript, Angular, VS Code IDE.

- YouTube.

- StackOverflow.

- W3Schools.

Project Schedule

Project Monitoring Mechanisms

- Note changes in design and new risks and requirements (also why and how they came in).

- Check and evaluate test cases and results.

- Implement SQA.

Software Development Model

Life Cycle Model: Iterative Model.

Stages:

- Requirement Gathering.

- Software Requirement Analysis.

- Software Design.

- Coding.

- Testing.

- Integration.

Project Schedule

- Work Break down

Tasks:

- Requirement Gathering (Functional, Non-Functional requirements etc.)

- Software Requirement Analysis.

- System Design (DFD’s, UML or Use-Case Model, WireFrame, UI design etc.)

- Coding:

  - User:

Welcome Page.

Registration Page.

Selection (Ballot) Page.

Result Page.

  - Admin:

Login Page/ Sign-up page

Enter Entities Page.

  - System:

Randomize Entities.

Create User-Entity(ballot) pairs after each selection(ballot).

Adjust Ballot data structure to indicate that an entity has been selected.

  - Development Testing.

- Testing:

  - System Testing.

  - Release Testing:

Requirement based-testing

Scenario testing.

Performance Testing.

  - User Testing: Beta Testing.

- Maintenance: Correct Issues with test.

- Integration: Hosting on intended server.

- Activity Table

| Task | Duration | Dependency |
| --- | --- | --- |
| T1: Requirement Gathering | 4hrs (1 day) |  |
| T2: System Analysis | 4hrs (1 day) | T1 |
| T3: Software Design | 8hrs (2 days) | T2 |
| T4: User Frontend | 4hrs | T3 |
| T5: User Backend | 6hrs | T3, T4 (T8 TBD from design) |
| T6: Admin Frontend | 4hrs | T3 |
| T7: Admin Backend | 4hrs | T3, T6 (T8 TBD from design) |
| T8: System | 4hrs | T5, T7 (T3 TBD from design) |
| T10: Testing | 4hrs | T8 (T5, T7 TBD from design) |
| T11: Maintenance | 4hrs | T10 |
| T12: Integration | 6hrs | T11 |

- Deliverables and Milestones

| Deliverable | Milestone |
| --- | --- |
| Software Requirement Specification | 26 June 2023 |
| System Analysis Document | 27 June 2023 |
| Software Design Document | 29 June 2023 |
| Fully Functioning Software (This encompasses all the deliverables from T4 – T8) | 5 July 2023 |
| Test Results | 6 July 2023 |
| Maintenance | 7 July 2023 |
| Integration | 9 July 2023 |

- Plan of Activities

| Date | Activity |
| --- | --- |
| 26 June 2023 | T1 |
| 27 June 2023 | T2 |
| 28 June 2023 | T3 |
| 30 June 2023 | Task C (Encompasses tasks T4 – T8) |
| 6 July 2023 | T10 |
| 7 July 2023 | T11 |
| 8 July 2023 | T12 |